Roles and Responsibilities

- Team Lead — coordinates schedule, ensures deadlines, compiles final files.

- Modeling Lead — builds frequency/severity and aggregate models for each hazard.

- Data Analyst — performs EDA, cleans data, documents limitations.

- Product Lead — drafts product design (triggers, exclusions, benefit structure).

- Risk Lead — creates threat table, correlated scenarios, stress tests.

- Writer / Editor — writes executive summary, ensures clarity and 10-page limit.

- Reviewer (non-technical) — final clarity/readability check (not required to know math).

Week-by-Week Task Plan (detailed)

Feb 6–8 Kickoff and Data Inventory

- Day 1: Kickoff meeting (60 min): confirm roles, share calendar, set communication channel.

- Deliverable: Single shared folder with all provided files; Data Inventory spreadsheet listing each file, sheet names, and immediate issues.

Feb 9–12 Exploratory Data Analysis and Cleaning

- Tasks:

  - Run EDA for each hazard: claim counts, claim amounts, exposures, missingness, outliers.

  - Create data issues log (missing fields, inconsistent IDs, currency units, truncated files).

  - Decide on treatment: imputation, exclusion, or assumption.

- Deliverable: EDA report (2–3 pages) + cleaned sample datasets.

Feb 13–16 Frequency and Severity Modeling

- Tasks:

  - Fit frequency models (Poisson/NegBin) using exposure as offset.

  - Fit severity distributions (lognormal, gamma, generalized Pareto for tails).

  - Validate fits with QQ plots, KS tests, and residual checks.

  - Document key assumptions and rationale.

- Deliverable: Model summary table (expected frequency, mean severity, variance) per hazard and per solar system.

Feb 17–19 Aggregate Modeling and Capital Tests

- Tasks:

  - Combine frequency and severity into aggregate loss distributions (Monte Carlo simulation).

  - Produce expected value, variance, 95th/99th percentiles, and 1-in-100-year loss.

  - Discount future losses using provided yield curve; apply inflation adjustments from dataset.

  - Run sensitivity checks on key assumptions (±10–20% on frequency/severity).

- Deliverable: Aggregate loss outputs and stress test results; short memo on discounting and inflation approach.

Feb 20–22 Product Design and Pricing Ranges

- Tasks:

  - For each hazard, propose one primary product and one optional rider. Include triggers, exclusions, limits, and deductible structure.

  - Translate aggregate loss outputs into premium ranges, target margin, and expected net revenue ranges.

  - Consider scalability and system-specific adaptations (e.g., higher debris coverage in Helionis).

- Deliverable: Product design table and pricing summary (expected premium, variance, net revenue range).

Feb 23–25 Risk Assessment and Scenario Testing

- Tasks:

  - Create a threat table ranking top 8–10 risks by likelihood and impact.

  - Define correlated scenarios (e.g., solar storm affecting Bayesia + Helionis) and run scenario losses.

  - Provide best/moderate/worst-case narratives and quantify financial impacts.

- Deliverable: Threat table, scenario loss table, and short narrative comparing solar systems.

Feb 26 Draft Report Assembly

- Tasks:

  - Writer assembles the 10-page body: Executive Summary, Product Design highlights, Pricing & Capital summary, Risk Assessment summary, Key Assumptions, Data Limitations.

  - Appendices: model details, charts, code snippets, full tables (these do not count toward 10 pages).

- Deliverable: Full draft (body + appendices).

Feb 27 Review and Final Edits

- Tasks:

  - Non-technical reviewer reads body for clarity; modeling lead verifies appendix numbers.

  - Ensure AI usage disclosure is written and included per rules.

  - Check formatting: 1-inch margins, 12-pt font, file size <25 MB.

- Deliverable: Finalized report and supporting files.

Feb 28 Submission Day

- Tasks:

  - Final file naming per rules; confirm cover page includes team name, university, and student names (no emails).

  - Upload via submission form; confirm receipt email within 15 minutes. If no confirmation, follow backup email instructions.

- Deliverable: Submission confirmation screenshot or saved email.

Modeling and Analysis Checklist

- Data: exposure aligned with claim counts; currency units consistent; truncated files flagged.

- Frequency: test Poisson vs Negative Binomial; include exposure offset.

- Severity: fit heavy-tail models; consider GPD for tail.

- Aggregation: Monte Carlo with at least 100k simulations; capture tail percentiles.

- Discounting: apply provided spot rates and inflation series; document method.

- Correlation: model dependence across systems using copula or scenario multipliers.

- Documentation: every assumption must have a one-line rationale and be listed in the body.

Communication, Appendices, and Submission Checklist

- Executive Summary: 1 page; state recommendations first, then 3 bullets of supporting evidence.

- Body: max 10 pages; use headings, short paragraphs, and visuals.

- Appendices: model formulas, code snippets, full tables, and references.

- AI Disclosure: one short paragraph in the Assumptions or Data Limitations section describing any AI use and validation steps.

- Final Checklist before upload: cover page present; 10-page body limit respected; bibliography included; file types and sizes compliant; faculty advisor listed; team registered.